## Sprint #1 Plan
User Stories | Tasks | Description | Dependency | Story Points | 1 | 2 | 3 | 4 | 5
1 | 1.1 | Write our Tools Specifications that we will be using to build the platform. Documentation of technology we are using. (Sheet Team Plan) |  | 4 | R:2 | R:2
1 | 1.2 | Create Heroku project and server. |  | 2 |  | B:2
1 | 1.3 | Set up Node.js backend on the Heroku server to show a simple web page containing HTML and CSS. | 1.2 | 4 |  |  | B:2 | B:2
1 | 1.4 | Set up functionality to accept CSV files, by this we mean create the function that will handle the click request |  | 2 |  |  |  |  | B:2
2 | 2.1 | Setup intial layout of web application, which involves node libraries/gitignores and standard files |  | 2 | D:2
2 | 2.2 | Create a simple HTML page with CSS styling (all with Bootstrap) which has a clickable upload button, with the X logo | 2.1 | 10 | C:2 | C:2 | C:2 | C:2 | C:2
2 | 2.3 | Create a simple HTML page with CSS styled (all with Bootstrap) with Login Page. | 2.1 | 10 | A:2 | A:2 | A:2 | A:2 | A:2
2 | 2.4 | Create a simple HTML page with CSS styled (all with Bootstrap) with Create Account Page. | 2.1 | 5
2 | 2.5 | Create a Navigation Bar Sticky Header at the top of the webpage | 2.1 | 5
3 | 3.1 | Flesh out the System Design of the Database Schema |  | 8 |  | D:2 | D:2 | D:2 | D:2
3 | 3.2 | Code Insert Report EndPoint (Accepts JSON Objects) (No DB Needed) |  | 2 | B:2
3 | 3.3 | Parse the json object element by element and insert it into the database | 3.2 | 14 |  |  | R:2 | R:2 | R:2
3 | 3.4 | Use Axios to make a post request to the endpoints to send data. | 3.2 | 8
3 | 3.5 | Read and parse data from an iCARE template, by using the npm package that converts csv to json | 1.4 | 8

## Execution Sprint #1
User Stories | Tasks | Description | Dependency | Story Points | 1 | 2 | 3 | 4 | 5
1 | 1.1 | Write our Tools Specifications that we will be using to build the platform. Documentation of technology we are using. (Sheet Team Plan) |  | 4 | R:2 | R:2
1 | 1.2 | Create Heroku project and server. |  | 2 |  | B:2
1 | 1.3 | Set up Node.js backend on the Heroku server to show a simple web page containing HTML and CSS. | 1.2 | 4 |  |  | B:2 | B:2 |  | Byron did not have time to work on his task on day 5
1 | 1.4 | Set up functionality to accept CSV files, by this we mean create the function that will handle the click request |  | 2 |  |  |  |  | B:0
2 | 2.1 | Setup intial layout of web application, which involves node libraries/gitignores and standard files |  | 2 | D:2 |  |  |  |  | D decided to work on 2.4 first, and finished it on the first day in 2 hours ... so he worked on the database schema on days 3 4 5, and was able to finish it in a total of 6 developer hours, he also finished 3.1 on itme
2 | 2.2 | Create a simple HTML page with CSS styling (all with Bootstrap) which has a clickable upload button, with the X logo | 2.1 | 10 | C:2 | C:2 | C:2
2 | 2.3 | Create a simple HTML page with CSS styled (all with Bootstrap) with Login Page. | 2.1 | 10 | A:2 | A:2 | A:2 | A:2 | A:2
2 | 2.4 | Create a simple HTML page with CSS styled (all with Bootstrap) with Create Account Page. | 2.1 | 5 |  | D:2
2 | 2.5 | Create a Navigation Bar Sticky Header at the top of the webpage | 2.1 | 5 |  |  |  | C:2 | C:2
C finished his 2.2 task earlier than expected, and so worked on the 2.5 task, but did not end of completing it
3 | 3.1 | Flesh out the System Design of the Database Schema |  | 8 |  |  | D:2 | D:2 | D:2
3 | 3.2 | Code Insert Report EndPoint (Accepts JSON Objects) (No DB Needed) |  | 2 | B:2
3 | 3.3 | Parse the json object element by element and insert it into the database | 3.2 | 14 |  |  | R:2 | R:2 | R:2
3 | 3.4 | Use Axios to make a post request to the endpoints to send data. | 3.2 | 8
3 | 3.5 | Read and parse data from an iCARE template, by using the npm package that converts csv to json | 1.4 | 10

## Burndown Sprint # 1
Days | 0 | 1 | 2 | 3 | 4 | 5
Provisial (in story points) | 50 | 46 | 40 | 40 | 36 | 6
Actual (in story points) | 50 | 46 | 35 | 25 | 21 | 3

## Sprint #2 Plan
User Stories | Tasks | Description | Dependency | Story Points | 1 | 2 | 3 | 4 | 5
1 | 1.4 | Set up functionality to accept CSV files, by this we mean create the function that will handle the click request (be able to upload) |  | 2 | B:2
2 | 2.5 | Create a Navigation Bar Sticky Header at the top of the webpage |  | 1 | C:1
2 | 2.6 | Create the landing page and hook it up to the navbar |  | 3 | C:1 | C:2
2 | 2.7 | Create the about us page and hook it up to the navbar |  | 4 | A:2 | A:2
2 | 2.8 | Create a page that contains history of events that the TEQ can see. Make the UI only. In future we will get the data from the database. |  | 4 |  |  |  | C:2 | C:2
2 | 2.9 | Create a logout button for the page that the organization member goes to after they login, the local storage should reflect that they log out |  | 2 |  |  | C:2
2 | 2.1 | Create a Grid using an NPM Package for the list of people in the organization |  | 6 |  |  | A:2 | A:2 | A:2
3 | 3.3 | Parse the json object element by element and insert it into the database |  | 8 | R:0 | R:2 | R:2 | R:2 | R:2
3 | 3.4 | Read and parse data from an iCARE template, by using the npm package that converts csv to json | 1.4 | 8 |  | B:2 | B:2 | B:2 | B:2
3 | 3.5 | Send Axios to make post request when logging into account with local storage setup |  | 2 | D:2
3 | 3.6 | Send Axios to make post request when creating organization account |  | 2 |  | D:2
3 | 3.7 | Send Axios to make post request when uploading file data |  | 6 |  |  | D:2 | D:2 | D:2

## Execution Sprint # 2
User Stories | Tasks | Description | Dependency | Story Points | 1 | 2 | 3 | 4 | 5
1 | 1.4 | Set up functionality to accept CSV files, by this we mean create the function that will handle the click request (be able to upload) |  | 2 |  |  | B:2 |  |  | C73 assignment, midterms
2 | 2.5 | Create a Navigation Bar Sticky Header at the top of the webpage |  | 1 | C:1
2 | 2.6 | Create the landing page and hook it up to the navbar |  | 3 | C:1 | C:1
2 | 2.7 | Create the about us page and hook it up to the navbar |  | 4 |  | C:1
2 | 2.8 | Create a page that contains history of events that the TEQ can see. Make the UI only. In future we will get the data from the database. |  | 4 |  |  |  | C:2 | C:2
2 | 2.9 | Create a logout button for the page that the organization member goes to after they login, the local storage should reflect that they log out |  | 2 |  |  | C:2
2 | 2.1 | Create a Grid using an NPM Package for the list of people in the organization |  | 6 | [5 empty] | Was not done, low priority
3 | 3.3 | Parse the json object element by element and insert it into the database |  | 8 | R:0 | R:2 | R:2 | R:2 | R:2
3 | 3.4 | Read and parse data from an iCARE template, by using the npm package that converts csv to json | 1.4 | 8 |  |  |  | B:4 | B:4
3 | 3.5 | Send Axios to make post request when logging into account with local storage setup |  | 2 | D:2
3 | 3.6 | Send Axios to make post request when creating organization account |  | 2 |  | D:2
3 | 3.7 | Send Axios to make post request when uploading file data |  | 6 |  |  | D:2 | D:2 | D:2

## Burndown Sprint # 2
Days | 0 | 1 | 2 | 3 | 4 | 5
Provisial (in story points) | 50 | 45 | 36 | 34 | 34 | 2
Actual (in story points) | 50 | 47 | 38 | 34 | 34 | 8

## Team Plan
| React + SC | JavaScript + CSS + HTML
Aliza | Styled Components | CSS
Bryon | JavaScript Front-End | Javascript
Caleb | Styled Components | CSS
Dharmik | JavaScript Front-End | JavaScript
Ralph | BackEnd + DataBase ( Node Express and NEDB/MongoDB) | Node/Express/MongoDB
Sprint #1 | Sprint #2
Wednesday - Sunday | Mon - Fri
Git Tutorial
Git Version Control | https://try.github.io/
How to Build & Style a Web Page |  | Caleb and Aliza google how to format a PDF with CSS
BootStrap (CSS Styling) | https://getbootstrap.com/
Using HTML and CSS, bootstrap | https://www.w3schools.com/html/html_css.asp
Jquery (Making Web Dev Faster) | https://jquery.com/
How to talk to back-end from FrontEnd
JSON OBJECTS (How data Goes over the web) | https://www.json.org/
Fetch or Axios Networking Libarary for Frontend | https://www.npmjs.com/package/axios
How backend receives information from Front End
Node.js | https://nodejs.org/en/
Express.js | https://expressjs.com/ | app.get('/', (req, res) => res.send('Hello World!')) | This endpoint is what the front end people will hit. So LocalHost:/ will return Hello World when hit with a GET request
How to Store Data
NEDB DataBase Technology | https://github.com/louischatriot/nedb
Where will our code be deployed
Heroku it's like a Web Server | https://www.heroku.com/ | When you push to master you will see updates at the URL Dharmik's Website.com | Ralph should set up CD
Packages
Grid Package | https://gijgo.com/grid/demos/bootstrap-4-table | https://www.npmjs.com/package/jquery-grid
Upload a CSV file, return a JavaScript Array | https://www.npmjs.com/package/csvtojson | This converts CSV Files to JSON Objects that we can send to the Server Automatically since it's a JSON Object
| /** csv file | Converts to JSON Object
| a,b,c | [
| 1,2,3 | * {a:"1", b:"2", c:"3"},
| 4,5,6 | * {a:"4", b:"5". c:"6"}
| */ | * ]
Helpful Links
Bryon's Task | https://stackoverflow.com/questions/4720343/loading-basic-html-in-node-js